## Slide 1
Ivan Marković
MSP Lead
Software Developer at SPAN d.o.o.
ivan.markovic@studentpartner.com

## Slide 2: Agenda
Waterfall or Agile
Scrum
ALM

## Slide 3: Waterfall or Agile

## Slide 4: Methodology vs framework
A methodology is a set of principles, tools and practices which can be used to guide processes to achieve a particular goal.
A framework is a loose but incomplete structure which leaves room for other practices and tools to be included but provides much of the process required.

## Slide 5
Waterfall development

## Slide 6
FBI ACS System
Built with 1970s-era software tools
Natural
ADABAS
IBM Green screens

## Slide 7
FBI – Virtual Case File
The Goal – Replace ACS
The Plan- Spec it and cotranct it on fixed bid
Science Applications International Corporation(SAIC) awarded primary software contract
Other vendors for smaller pieces
The Projection
3 years
$ 380m

## Slide 8
2001 – Coding starts
January 2005 – All code scrapped
$170m spent
FBI – Virtual Case File

## Slide 9: FBI – Virtual Case File
FBI Director Robert
Mueller asked congress
for more money to
keep going
Three times
Start over!

## Slide 10: Sentinel
2006 Lockheed Martin wins software contract
The NEW Plan:
4 phases
$450m
6 years

## Slide 11: Sentinel
Really hopeful this time

## Slide 12: Sentinel
2010
1.5 phase done
$421m spent
2 years remain

## Slide 13: Sentinel
They need another $351m and 6 years

## Slide 14: Sentinel Scrums
2010
2011
2012
Jeff Johnson
Chad Fulghram
FBI cancels contract with external software vendors
Software complete- Dec 2011
$30m spent
All field tests passed and complete- May ‘12
Long wait for proprietary hardware

## Slide 15: Agile
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan

## Slide 16
Waterfall development
Pros
Clear plan/clear vision
Accurately estimate timetable and budgets
Plan oriented -> More secure
Cons
Rigid
Inflexible
Problem with late testing and feedback

## Slide 17: Agile development
Pros
Cons
Flexible, adaptive
No clearly defined end-goals
Collaboration
Feedback
Lack of structure
Quite time consuming (customer involvment)
Possible person drop is problem

## Slide 18: Waterfall vs Agile

## Slide 19: Scrum

## Slide 20: Scrum is..
A framework for Agile software development
A set of rules
Easy to learn
Difficult to master

## Slide 21: Scrum is used for
Managing the work of: small teams, large organizations, everything in between
Fixed-price work
Developing software of every type imaginable

## Slide 22: Scrum

## Slide 23: Sprints
Scrum projects make progress in a series of “sprints”
Typical duration is 2–4 weeks or a calendar month at most
A constant duration leads to a better rhythm
Product is designed, coded, and tested during the sprint

## Slide 24: Roles
Product owner
Scrum Development team (3-9 people)
Scrum Master

## Slide 25: Development team
5-9 people
Programmers, testers, user expirience designers, etc.
Teams are self-organizing

## Slide 26: Ceremonies
Sprint planning
Sprint review
Sprint retrospective
Daily scrum meeting

## Slide 27: Sprint planning
Team selects items from the product backlog they can commit to completing
Sprint backlog is created
  Tasks are identified and each is estimated (1-16 hours)
  Collaboratively, not done alone by the ScrumMaster
High-level design is considered

## Slide 28: The daily scrum
Parameters
  Daily
  15-minutes
  Stand-up
Not for problem solving
  Whole world is invited
  Only team members, ScrumMaster, product owner, can talk
Helps avoid other unnecessary meetings

## Slide 29: The daily scrum
What did you do yesterday?
What will you do today?
Is anything in your way?

## Slide 30: The sprint review
Team presents what it accomplished during the sprint
Typically takes the form of a demo of new features or underlying architecture
Informal
  2-hour prep time rule
  No slides
Whole team participates
Invite the world

## Slide 31: Sprint retrospective
Periodically take a look at what is and is not working
Typically 15–30 minutes
Done after every sprint
Whole team participates
  ScrumMaster
  Product owner
  Team
  Possibly customers and others

## Slide 32: Artifacts
Product backlog
Sprint backlog

## Slide 33: Product backlog
The requirements
A list of all desired work on the project
Ideally expressed such that each item has value to the users or customers of the product
Prioritized by the product owner
Reprioritized at the start of each sprint
This is the product backlog

## Slide 34: Developer vs Project Manager
http://www.youtube.com/watch?v=ptCzqugFn_w

## Slide 35: ALM
Microsoft ALM

## Slide 36: What is ALM?
ALM = Application Lifecycle Management
Microsoft’s view of ALM
  Plan and Track
  Design
  Develop
  Automated Build
  Testing
  Test Lab Management

## Slide 37: Visual Studio
Integrated development environments (IDE)
Visual Studio Express – free
http://www.visualstudio.com/en-us/products/visual-studio-express-vs.aspx

## Slide 38: Team Foundation Server
Version Control
Agile Planning & Collaboration
Build
Test Case Management
Reporting

## Slide 39: Team Foundation Version Control vs GIT
FEATURE | TFS | GIT
Save source code | Yes | Yes
Version history | Yes | Yes
Offline commit | No | Yes
GUI Support | Strong | Poor
Analytics and charting | Yes | No
Installation | ½ day | 10 minutes
Cost | $$$ | Free

## Slide 40: Visual Studio Online
Based on the capabilities of Team Foundation Server
5 users FREE (VS Online Basic)
$20 per additional user, per month
Access your code from anywhere

## Slide 41: VS Online+TFS+VS+Power Point
Demo...

## Slide 42: Q & A
?

## Slide 43: What’s next?
15.11. – Poslovni plan, Sunčica Oberman Peterka (EFOS)
  Radionica: Osmišljavanje ideja po grupama, pisanje kratkog plana
  19.11. – C#... , Igor Ralić (dizzy.hr)

## Slide 44
Thank you!
ivan.markovic@studentpartner.com